## TY2022 Open&Resolved
Known Issues and Solutions
Date | Tax Year | Form Type | Issue Type | Description of Issue | Workaround | Projected Resolution Date | Date Resolved | Status
2023-12-18 | 2022 | Form 1040 | Schema | Elements ‘Form8854DeferredTaxGrp’, ‘TotalTaxDeferredAmt’ and ‘ExpatriationCd’ in the 1040 schema are on line 23 instead of line 24 as instructed on Form 8854 Section D, line 5. | No impact to processing. Continue to use the three elements when applicable. The schema will be updated for TY2024 in PY2025. | 2025-01-01 |  | OPEN
2023-07-24 | 2022 | Schedules K-2 and K-3 | Schema | 1065 and 8865 Schedules K-2 and K-3, Part IV, Section 3, Lines 14A - 14F uses efileType USAmountNNType (non-negative values). | If adjustments result in negative values for Part IV, Section 3, Lines 14A - 14F, report these amounts in a separate statement attached to your return. | 2025-01-01 |  | OPEN
2023-03-01 | 2022 | Form 8822-B | Dependency | For Tax Year 2022 indicators were added to ensure that the responsible party information was current with the IRS. IRS regulations require any entity with an EIN to update the Responsible Party information within 60 days of any change by filing Form 8822-B, Change of Address or Responsible Party - Business. However, many of the Forms 8822-B that have been submitted do not reflect a change to the responsible party. | Form 8822-B should only be attached in an MeF submission to update the responsible party. The form should not be attached for any other reason. Any change of address should be reflected in the entity portion of the return with the appropriate address change indicator. | 2025-12-31 |  | OPEN
2023-01-23 | 2022 | Form 8889 | Stylesheet | Line 2 should display: HSA contributions you made for 2022 (or those made on your behalf), including those made by the un-extended due date of your tax return. Do not include employer contributions, contributions through a cafeteria plan, or rollovers. See instructions. | No impact at this time. | 2025-01-01 |  | OPEN
2022-11-10 | 2022 | Form 8839 | Schema | Form 8839 schema still has 'employerAdoptionBnftExclPYCd' with the enumeration “PYAB” and 'employerAdoptionBnftExclPYAmt'. Please continue to use the existing schema and follow the Form 8839 instructions for Tax Year 2022. | No impact at this time. | 2025-01-01 |  | OPEN
2022-10-25 | 2022 | Form 8997 | Stylesheet | A Work Request Notification (WRN) was issued 10/21/22 that contained verbiage changes to: Part II - "Applicability of Special Rules Regarding the Waiver of Certain Treaty Benefits" and the "Waiver of Treaty Benefits on Future Inclusions by a Foreign Eligible Taxpayer (for Tax Years Beginning After March 13, 2020, Only) sections; therefore, the latest form will not match the stylesheet for these lines | Form verbiage will differ until the fix is implemented; no impact to filing | 2024-06-30 |  | OPEN
2022-09-12 | 2022 | Form 1040 (SCH EIC) | Business Rules | Self-Only Earned Income Credit filers who qualify with a dependent that has an ATIN or ITIN cannot enter this number on Line 2 of Schedule EIC without triggering Business Rule SEIC-F1040-001-02. | If taxpayers are using a dependent that has an ATIN or ITIN to qualify for the Self-Only EIC per the instructions, they should leave Line 2 of Schedule EIC blank at this time. | 2025-01-01 |  | OPEN
2024-03-26 | 2022 | Form 1040 (SCH C) | Business Rules | Business rule SC-F1040-023 is rejecting when Schedule C losses are limited due to passive activity limitations (Form 8582) or at-risk limitations (Form 6198) on line 31. | The Business Rule SC-F1040-023 has been re-disabled for TY2023 and TY2022 as of March 26, 2023. It will be modified and re-enabled at a future date to account for taxpayers filing IRS forms 6198 and 8582. | 2025-01-01 | 2024-03-26 | RESOLVED
2024-03-08 | 2022 | Form 1040 | Business Rules | We are aware of a programming issue for the update that was delivered for Business Rule F1040-034-07. It applies to TY2021, TY2022 and TY2023, but F1040-034-07 is currently disabled for TY2021 and TY2022 and active for TY2023. | Business rule 1040-034-07 will revert to the previous verbiage for TY2021 and TY2022 and will be re-enabled. Form 1040, 'WithholdingTaxAmt' must be equal to the sum of the following: [(1) all 'WithholdingAmt' in [OtherWithholdingStatement] and (2) all Forms W-2, 'WithholdingAmt' and (3) all Forms W-2G, 'FederalIncomeTaxWithheldAmt' and (4) Form 8959, 'AddlMedcrRRTTaxWithholdingAmt' and (5) 'TotalAmt' in [BackupWhSchedulesK1Statement] and (6) all Forms RRB 1042-S, 'FederalIncomeTaxWithheldAmt' and (7) all Forms SSA 1042-S, ('NetTaxWithheldAmt' if it has a non-zero value, otherwise 'FederalIncomeTaxWithheldAmt')] unless Form 8958 is present in the return. When evaluating this, a tolerance of $5.00 is allowed. | 2024-03-17 | 2024-03-17 | RESOLVED
2023-07-27 | 2022 | Form 8283 | Stylesheet | Form 8283 Part II is not displaying correctly on the form. | The stylesheet will be corrected for TY 2023. | 2024-01-01 | 2024-01-31 | RESOLVED
2023-07-13 | 2022 | Form 8974 | Schema | A PDF Form 8974 is being filed at the same time the schema Form 8974 is being completed. | The PDF Form 8974 should not be filed as the the form is available in XML and should be filed that way. | 2024-01-30 | 2024-01-30 | RESOLVED
2023-06-27 | 2022 | Form 1118 (SCH I) | Schema | The element ‘ForeignCorpMissingEINReasonCd’ was erroneously left in the Form 1118 Schedule I Schema for Tax Year 2022. | The schema for Form 1118 Schedule I should be corrected to remove the element ForeignCorpMissingEINReasonCd before production begins for TY2023. In the meantime, Software developers can input the enumeration "FOREIGNUS" for the element "ForeignCorpMissingEINReasonCd" for Form 1118 Schedule I submissions that do not have a a ForeignCorporationEIN. | 2024-01-01 | 2023-11-13 | RESOLVED
2023-06-27 | 2022 | Form 1120-F | Stylesheet | Questions U1, U2, V, and HH are displaying correctly in the stylesheet but incorrectly in the schema i.e.,Yes (true in xml terms) on the stylesheet but the xml actually reflects values of false (which would translate to No on the stylesheet) for each of these elements. Questions are incorrectly using one element name instead of four different element names to display data. | Stylesheet/schema error will be updated in a future release. | 2024-01-01 | 2024-01-16 | RESOLVED
2023-05-03 | 2022 | Form 1040 | Business Rules | We are aware that the Business Rule F1040-071-07 is rejecting submissions when a Tax Treaty exemption is claimed on line 8z of Schedule 1. | Business Rule F1040-071-07 will be updated in PY2024. For taxpayers filing Exempt income from a treaty should file by paper until rule is updated. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-04-26 | 2022 | Form 8974 | Business Rules | The Form 8974 rule Form 8974-001, Line 11 'AdjSocialSecurityTaxTipAmt' must be equal to Line 10 'TotalSocialSecurityTaxTipAmt' multiplied by 50% (0.50).Is causing returns to reject due to the filers that have the box Third Party and/or the 3121q being checked. | The business rule will be disabled. Returns with this issue will need to be filed by paper until the rule is disabled. | 2023-05-31 | 2023-06-05 | RESOLVED
2023-04-13 | 2022 | Form 1040 | Stylesheet | Form 1040 line 19 is not populating in the stylesheet. | Form 1040 is displaying a blank for field 19 (Child Tax Credit and Other Dependent Credit Amount).If taxpayer entry information is needed, subtract 1040, Line 20 from Form 1040, line 21 to determine the Child Tax Credit and Other Dependent Credit amount on Form 1040, line 19. | 2023-06-18 | 2023-06-18 | RESOLVED
2023-04-13 | 2022 | Form 1040 (SCH 1) | Business Rules | Form 8853, line 26 amount can't be reported on Form 1040-NR Schedule NEC, line 12 instead of Schedule 1, line 8e, to report Non-Effectively Connected Income. | Form 1040-NR filers who need to report Form 8853, line 26 amount on Schedule NEC, line 12, should file by paper. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-04-11 | 2022 | Form 1120-S | Business Rules | Business rules F1120S-018-01 and F1120S-019-01 will be updated to include a reference to a binary attachment "IRA22DPE" or "CHIPS22DPE" as applicable. | The new business rules F1120S-018-02 and F1120S-019-02 are included in TY2022v5.2 | 2023-03-19 | 2023-04-11 | RESOLVED
2023-04-11 | 2022 | Form 8960 | Business Rules | Business Rules F8960-019-04 and F8960-003 were causing returns to erroneously reject and were disabled on 2/19/2023 in efile1040x_2022v5.2 Rules Sets. This was due to the rules not reflecting the updates to the Instructions for Form 8960 (Tax Year 2022) regarding the Specific Instructions for Line 4a to include Schedule C (Form 1040) amounts reported on Schedule 1 (Form 1040), line 3 and Form 1041, line 3. | Business Rules F8960-019-05 and F8960-003-01 were created with an implementation date of 2/19/2023. The updated business rules will be in change pages that will be available via the Secure Object Repository (SOR) in early to mid-March 2023.Rule Number: F8960-003-01 Rule Text: If Form 8960, 'NetRentalIncomeOrLossAmt' has a non-zero value, then it must be equal to the sum of Form 1041, 'NetProfitOrLossAmt' and 'NetRentalIncomeOrLossAmt'.Rule Number: F8960-019-05 Rule Text: If Form 8960, 'NetRentalIncomeOrLossAmt' has a non-zero value, then it must be equal to sum of Schedule 1 (Form 1040), 'BusinessIncomeLossAmt' and 'RentalRealEstateIncomeLossAmt' unless all of the following conditions are true: 1) Filing status of the return is Married filing jointly or Qualifying widow(er) and 2) Form 8960, checkboxes 'Section6013gInd' and 'Section6013hInd' are not checked and 3) Form 8960, 'FilingThresholdAmt' equals 125000. | 2023-03-19 | 2023-04-11 | RESOLVED
2023-04-10 | 2022 | Form 1120-F | Business Rules | Business rule F1120F-076-03 will be updated to include a reference to a binary attachment with description containing "IRA22DPE" or "CHIPS22DPE" as applicable. | Business rule was modified to F1120F-076-04 and is included in TY2022v5.2. | 2023-03-19 | 2023-04-10 | RESOLVED
2023-03-20 | 2022 | Form 8915-F | Schema | Form 8915-F Part I Disaster table column headers have been updated. The previous table requested Disaster FEMA number, Disaster beginning date and Disaster Ending date. The new table requests Disaster FEMA number, disaster declaration date and Disaster beginning date. The form was updated due to SECURE Act legislation passed December 2022. | The schema elements cannot be updated until next year. Please use element name 'DisasterBeginDt for the column header "Disaster Declaration date". Please use element name 'DisasterEndDt' for the column header "Disaster beginning date". | 2024-01-01 | 2024-01-16 | RESOLVED
2023-03-08 | 2022 | Schedules K-2 and K-3 | Dependency | Part I, Box 10, Partner Loan Transaction, Table 3, Upstream Loans, column title has changed from "Interest Expense" to "Interest Income." | Enter the value for Interest Income in the 'InterestExpenseAmt' field of SchedulesK2K3LoanTransactionsStatement. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-03-08 | 2022 | Form 1120 | Schema | Deemed Payment Election | Please use OtherRefundableCreditsAmt for the write-in and to report the amount | 2024-03-17 | 2024-01-19 | RESOLVED
2023-03-08 | 2022 | Form 1120-L | Schema | Deemed Payment Election | Please use TotalUndistributedLTCapGainAmt for the write-in and to report the amount | 2024-03-17 | 2024-01-19 | RESOLVED
2023-03-06 | 2022 | Form 8915-F | Stylesheet | Part I Line 1a, Page 2. The Secure Act legislation is allowing 22,000 for major disasters having a beginning date after January 25, 2021. The stylesheet for Form 8915-F does not reflect the following changes to the instructions for Part I, line 1a on page 2. See line 1a below to determine whether you need to complete lines 1a through 1e. You must use Worksheet 1B in the instructions if you are directed to do so in line 1a. However, you can always choose to use Worksheet 1B.a (i) If you checked 2021 in item A and 2020 in item B, do one of the following.• If either you didn’t file 2020 Form 8915-E or, on 2020 Form 8915-E, you only reported disasters other than those listed in the Part I Disaster Table earlier, skip lines 1a through 1d, and on line 1e enter $100,000 times the number of disasters you entered in the Part I Disaster Table.• Otherwise, complete lines 1a through 1e, entering on line 1a $100,000 times the number of disasters you entered in the Part I Disaster Table that were also reported on 2020 Form 8915-E, but do not include the coronavirus.(ii) If you checked 2021 or later in both item A and item B, do one of the following.(For 2021 and later disasters, the limit is $22,000, not $100,000, per disaster.)• If you listed only one disaster in the Part I Disaster Table and a prior year’s Form 8915-F doesn’t list that disaster in item C, skip to line 1e and enter $22,000 there.• If you listed only one disaster in the Part I Disaster Table and a prior year’s Form 8915-F lists that disaster in item C, complete lines 1a through 1e, entering $22,000 on line 1a. • If all of the distributions for this year occurred within the qualified disaster distribution period for each of the disasters listed in the Part I Disaster Table, complete lines 1a through 1e, entering on line 1a $22,000 times the number of disasters you entered in the Part I Disaster Table that were also entered in item C on a prior year’s Form 8915-F. | No impact at this time | 2024-01-01 | 2024-01-16 | RESOLVED
2023-03-06 | 2022 | Form 8915-F | Schema | Part I Line 1a (column b) and Line 1d (column b) schema description has a reference of 100,000. The Secure Act legislation is allowing 22,000 for major disasters having a beginning date after January 25, 2021. | Please disregard the schema description and enter the appropriate amount for Line 1a (column b) and line 1d (column b). | 2024-01-01 | 2024-01-16 | RESOLVED
2023-03-06 | 2022 | Form 8915-F | Stylesheet | Part I line 1d, Page 2. The Stylesheet for Form 8915-F does not reflect the following changes to the instruction for Part I, line 1d on page 2: Enter $22,000 ($100,000 if you checked 2020 in item B) times the number of qualified disasters that you entered in the Part I Disaster Table but didn’t enter in item C on a prior year’s Form 8915-F, or in Part I of 2020 Form 8915-E if you checked 2020 in item B . | No impact at this time | 2024-01-01 | 2024-01-16 | RESOLVED
2023-03-01 | 2022 | Form 1120 | Business Rules | New Business Rule FPYMT-052-01 is listed on the 1120_Amd_Business_Rules_Publication_2022v5.2 spreadsheet. The rule reads: If IRS Payment Record is present, then ‘PaymentAmt’ in the IRS Payment Record must be equal to Form 4868, line 7 ‘TaxpayerIsPayingAmt’. Form 4868 is the extension payment voucher for Individual returns and is not applicable to 1120 returns. | This rule does not apply to F1120 and will be removed in the upcoming business rule package and 1120_Amd_Business_Rules_Publication_2022v5.2_updated spreadsheet will be updated. | 2023-04-20 | 2023-04-20 | RESOLVED
2023-02-24 | 2022 | Form 8996 | Business Rules | Business Rule F8996-010 may cause returns to erroneously reject when Form 8996, Part II, Lines 7-9 do not apply | Business rule will be disabled until a fix can be implemented. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-02-16 | 2022 | Schedules K-2 and K-3 | Business Rules | Business Rule SK2-F1065-011 may cause returns to erroneously reject when values are present in Part IV. | Business rule will be disabled until a fix can be implemented. Rule disabled as of 3/19/2023. | 2023-06-18 | 2023-06-20 | RESOLVED
2023-02-16 | 2022 | Schedules K-2 and K-3 | Business Rules | Business Rules SK2-F1065-021 and SK3-F1065-021 may cause returns to erroneously reject when values are present in Part IX. | Business rules will be disabled until a fix can be implemented. Rule disabled as of 3/19/2023. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-02-16 | 2022 | Schedules K-2 and K-3 | Business Rules | Business Rules SK2-F1065-023 and SK3-F1065-023 may cause returns to erroneously reject when values are present in Part X. | Business rules will be disabled until a fix can be implemented. Rule disabled as of 3/19/2023. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-02-08 | 2022 | Form 1040 (SCH C) | Schema | Line B is a choice of the Unclassified Established Code,'999999' or the Principal Business Activity Code, '999000'.The tax year 2022 F1040 Schedule C Instructions state to use only code '999000' for the Unclassified Established Code. | The schema will allow both codes for the 2022 tax year. PrincipalBusinessActivityCd should be represented with '999000' and the UnclassifiedEstablishmentCd should be represented with code ‘999999’. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-02-07 | 2022 | Form 2441 | Business Rules | Business Rule F2441-029 is currently disabled in efile1040x_2022v5.2 Rules Sets. | Business Rule F2441-029 is being modified. The updated business rule will be in change pages that will be available via the Secure Object Repository (SOR) in early to mid-March 2023. | 2023-03-19 | 2023-03-19 | RESOLVED
2023-02-07 | 2022 | Form 8864 | Business Rules | Business Rule 8864-10 needs to be fixed because it is causing returns to be rejected.The schemas for the Forms 1040, 1040NR, 1041 and 1120 have all been updated to fix the Business Rule 8864-10 but the SOR had not been updated for the Form 1065. | The Business Rule 8864-10 has been updated in the schemas for the Forms 1040, 1040NR, 1041, 1065 and 1120. The SOR package for the Form 1065 2022v4.2 was not updated but the schema was updated. | 2023-06-30 | 2023-06-05 | RESOLVED
2023-02-07 | 2022 | Form 1116 | Business Rules | For Tax Year 2022 Processing Year 2023 the naming convention has been updated to allow multiple Forms 1116, Schedule B. For example: F1116ScheduleB1, F1116ScheduleB2 or F1116 ScheduleB, F1116 ScheduleB1, or F1116Schedule B, F1116Schedule B1. By giving each Form 1116, Schedule B a different name the system will allow up to 999 different Form 1116, Schedule Bs to be attached the line 10 level. | This is a change to line 10 of the Form 1116 to allow multiple Forms 1116, Schedule B to be attached at the line level. | 2024-01-30 | 2024-01-30 | RESOLVED
2023-02-07 | 2022 | Form 1120-S | Schema | Deemed Payment Election | Please use the special condition description for the write-in and to report the amount. | 2024-03-15 | 2024-01-19 | RESOLVED
2023-02-07 | 2022 | Form 1120-PC | Schema | Deemed Payment Election | Please use the OtherCreditsAndPaymentsStatement for the write-in and to report the amount. | 2024-03-15 | 2024-01-19 | RESOLVED
2023-02-02 | 2022 | Form 461 | Stylesheet | Form 461 line 16 references Schedule 1 (1040) line 8o. The correct reference should be Schedule 1(1040) line 8p. | Please carry the amount from Form 461 line 16 to Schedule 1 (1040) line 8p. | 2024-01-01 | 2024-01-16 | RESOLVED
2023-02-01 | 2022 | Form 1040-NR | Stylesheet | Form 1040-NR line 19 is not populating in the stylesheet. | If taxpayer entry is needed for Form 1040-NR, line19, the amount on Schedule 8812, line 14, can be used. | 2023-04-30 | 2023-03-19 | RESOLVED
2023-02-01 | 2022 | Form 1040 (SCH 8812) | Stylesheet | Schedule 8812 (Form 1040) is displaying a blank for field 16b (Number of qualifying children). | If taxpayer entry is needed, the amount on 16b can be divided by 1,500 to determine the number of qualifying children on line 16b. | 2023-06-18 | 2023-06-18 | RESOLVED
2023-02-01 | 2022 | Form 1040 (SCH 8812) | Stylesheet | Schedule 8812 (Form 1040) is displaying a blank for line 12, and the line 12 amount is populating on line 13. Line 13 amount is populating to line 14 and the line 14 amount is not populating on the stylesheet. | To determine the amounts on line 12,13 and 14 reference the XML. | 2024-01-01 | 2023-11-28 | RESOLVED
2023-01-31 | 2022 | Form 1065 | Schema | Deemed Payment Election | Form 1065 use the special condition description to report the write-in and amount. | 2024-03-15 | 2024-03-15 | RESOLVED
2023-01-31 | 2022 | Form 3468 | Dependency | Form 3468 line 12dd did not receive the schema update to include a statement attachment. It must include: 1. Your name, address, taxpayer identification number, and telephone number.2. For each qualified investment credit facility, include the following: a. A detailed technical description of the facility, including generating capacity. b. A detailed technical description of the energy property placed in service during the tax year as an integral part of the facility, including a statement that the property is an integral part of such facility. c. The date that the energy property was placed in service. d. An accounting of your basis in the energy property. e. A depreciation schedule reflecting your remaining basis in the energy property after the energy credit is claimed. 3. A statement that you haven't and won't claim a Section 1603 grant for new investment in the property for which you are claiming the energy credit. 4. A declaration, applicable to the statement and any accompanying documents, signed by you or signed by a person currently authorized to bind you in such matters that states the following: "Under penalties of perjury, I declare that I have examined this statement, including accompanying documents, and to the best of my knowledge and belief, the facts presented in support of this statement are true, current, and complete." | An attachment is required to explain the catch all credits, per the new instructions, and this explanation will be attached at the form level. When naming the explanation the following naming convention can be used::Line12ddexplanationLine12ddexplanation1 | 2024-01-30 | 2024-01-30 | RESOLVED
2023-01-31 | 2022 | Form 3468 | Dependency | Form 3468 line 12hh did not get the schema updated to include a statement attachment. It must include 1. Your name, address, taxpayer identification number, and telephone number. 2 For each qualified investment credit facility, include the following: a. A detailed technical description of the facility, including generating capacity. b. A detailed technical description of the energy property placed in service during the tax year as an integral part of the facility, including a statement that the property is an integral part of such facility. c. The date that the energy property was placed in service. d. An accounting of your basis in the energy property. e. A depreciation schedule reflecting your remaining basis in the energy property after the energy credit is claimed. 3. A statement that you haven't and won't claim a Section 1603 grant for new investment in the property for which you are claiming the energy credit. 4. A declaration, applicable to the statement and any accompanying documents, signed by you or signed by a person currently authorized to bind you in such matters that state the following: "Under penalties of perjury, I declare that I have examined this statement, including accompanying documents, and to the best of my knowledge and belief, the facts presented in support of this statement are true, current, and complete." | An attachment is required to explain the catch all credits, per the new instructions, and this explanation will be attached at the form level. When naming the explanation the following naming convention can be used::Line12hhexplanationLine12hhexplanation2 | 2024-01-30 | 2024-01-30 | RESOLVED
2023-01-26 | 2022 | Schedules K-2 and K-3 | Business Rules | Business Rule SK2-F1065-009 may cause returns to erroneously reject when values are present in Part III. | Business rule will be disabled until a fix can be implemented. Rules disabled as of 1/23/2023. | 2023-06-18 | 2023-06-20 | RESOLVED
2023-01-26 | 2022 | Schedules K-2 and K-3 | Business Rules | Business Rule SK3-F1065-009 may cause returns to erroneously reject when values are present in Part III. | Business rule will be disabled until a fix can be implemented. Rules disabled as of 1/23/2023. | 2023-06-18 | 2023-06-20 | RESOLVED
2023-01-26 | 2022 | Schedules K-2 and K-3 | Schema | Partner/Shareholder TIN does not allow for situations when the partner/shareholder doesn't have a U.S. identifying number. | If the partner/shareholder doesn’t have a U.S. identifying number, enter “999999999” for the partner’s/shareholder’s identifying number. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-01-26 | 2022 | Schedules K-2 and K-3 | Business Rules | Business Rule SK3-F1065-011 may cause returns to erroneously reject when values are present in Part IV. | Business rule will be disabled until a fix can be implemented. Rule disabled as of 2/19/2023. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-01-24 | 2022 | Form 1040-PR | Stylesheet | Form 1040-PR is displaying the information from Tax Year 2021. | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-01-19 | 2022 | Form 1040 (SCH F) | Stylesheet | Line 6c should display: If election to defer to 2023 is attached, check here… | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-01-19 | 2022 | Form 1040 (SCH F) | Stylesheet | Line 34 Third sentence should display: If a loss, complete line 36. | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-01-18 | 2022 | Form 1040 | Business Rules | We are aware that BR 1040-071-07 will reject when Form 1040 line(s) 1g and/or 1h are populated with federal tax withholding reported. Please hold the returns meeting this condition until the Business Rule is fixed. | Business Rule F1040-071-07 will be updated in early PY2023. | 2023-02-28 | 2023-02-19 | RESOLVED
2023-01-18 | 2022 | Form 8835 | Business Rules | Business Rule F8835-015 currently contains an incorrect reference to 'Sect45VSpecialAdjustments'. This element name should be 'Sect45VSpecialAdjustmentsAmt'. | Business Rule F8835-015 will be updated in early PY2023. | 2023-03-19 | 2023-03-19 | RESOLVED
2023-01-12 | 2022 | Form 1120-F | Schema | Deemed Payment Election | Form 1120-F use the special condition description to report the write-in and amount. | 2024-01-01 | 2023-03-20 | RESOLVED
2023-01-12 | 2022 | Form 1120-F (SCH P) | Stylesheet | Page 3 Part V Column heading should display: Partnership Interest Transferred (see instructions) | No impact at this time. | 2023-03-15 | 2023-04-11 | RESOLVED
2023-01-12 | 2022 | Form 1120-F (SCH P) | Stylesheet | Page 3 Part IV Heading should display: Foreign Partner's Interests in Partnerships Transferred During Tax Year | No impact at this time. | 2023-03-15 | 2023-04-11 | RESOLVED
2023-01-12 | 2022 | Form 5472 | Stylesheet | Page 3 Line 40b should display: If "Yes," enter the total amount of the disallowed deductions | No impact at this time. | 2024-01-01 | 2023-03-21 | RESOLVED
2023-01-12 | 2022 | Form 5472 | Stylesheet | Page 3 Line 47 should display: What was the reporting corporation's share of reasonably anticipated benefits for the CSA? | No impact at this time. | 2024-01-01 | 2023-03-21 | RESOLVED
2023-01-12 | 2022 | Form 1120-F | Schema | Deemed Payment Election | Form 1120-F use the special condition description to report the write-in and amount. | 2024-01-01 | 2024-01-16 | RESOLVED
2023-01-10 | 2022 | Form 1040 (SCH 1) | Business Rules | Business Rule S1-F1040-396 should be updated to reflect the Tax Year 2022 threshold amount for Married Filing Jointly from 170,000 to 175,000. | Taxpayers who have a modified adjusted gross income greater than 170,000 and up to 175,000 will need to hold these types of returns until after the Business Rule has been updated. | 2023-02-19 | 2023-02-19 | RESOLVED
2023-01-06 | 2022 | Form 8959 | Stylesheet | Form 8959 Stylesheet is displaying the filing status Qualifying Widow(er) instead of Qualifying Surviving Spouse. | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2023-01-06 | 2022 | Form 8863 | Stylesheet | Form 8863 Stylesheet is displaying the filing status Qualifying Widow(er) instead of Qualifying Surviving Spouse on lines 2, 5, 13 and 16. The stylesheet for lines 3 and 14 does not have the word "instead" in the sentence. Lines 3 and 14 should read:Enter the amount from Form 1040 or 1040-SR, line 11. But if you’re filing Form2555 or 4563, or you’re excluding income from Puerto Rico, see Pub. 970 for the amount to enter instead.Part III incorrectly enumerates line 22 twice, when Student Social Security Number should be line 21 instead of line 22.Line 23 should read:Has the American opportunity credit been claimed for this student for any 4 prior tax years? | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-29 | 2022 | Form 1065 (SCH K-1) | Schema | Schedule K1 (1065), Part III, Box 20 is a required field which causes problems for TPs that do not have a dollar amount but need to attach a statement. | Enter 0 on the dollar amount for Schedule K1 (1065) Part III, Box 20 and attach the statement | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-23 | 2022 | Schedules K-2 and K-3 | Schema | Part I, Box 1 instructions revise Table 1 (SchedulesK2K3PersonalPropertySoldStatement) by removing columns for Date of Sale, Proceeds, and Basis. New columns are added for Long-term/short-term and Gains. | Do not enter values in 'SaleDt', 'ProceedsAmt', or 'BasisAmt' elements. Enter values for new columns (b) Long-term/short-term and (c) Gains in 'ExplanationTxt' field. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-23 | 2022 | Schedules K-2 and K-3 | Schema | Part III, Section 4, Line 1, 'DrtSect901Or903FrgnTxsGrp' (1120-S Section 3, Line 1, 'DrtSect901Or903FrgnTxsShrGrp') is limited to 100 entries. | If more than 100 entries are required, attach a General Dependency or Binary Attachment with the additional information. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-23 | 2022 | Schedules K-2 and K-3 | Schema | Part III, Section 2 instructions require an additional Section 2 if the filer reports both the tax book value and the alternative tax book value of its assets. However, the schema is limited to 1 instance of Section 2. | If an additional instance of Section 2 is required, attach a General Dependency or Binary Attachment with the additional information. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-23 | 2022 | Schedules K-2 and K-3 | Schema | Part VII, Section 1, column (j), 'PartnershipElectionCd' (Part VI, 1120-S, 'CorporationElectionCd'), "QIC" is no longer valid entry. | Do not enter "QIC" in 'PartnershipElectionCd' ('CorporationElectionCd', 1120-S). | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-19 | 2022 | Form 1116 | Schema | Form 1116, Part I, Columns iA, iB, iC choice for ForeignRegulatedInvestmntCompCd only allows “RIC”, “965”, “951A”. If the options are not chosen, then no other enumerations to be entered on that line. | For this field, enter “Income” as any of the following “RIC”, “965” or “951A” if no enumerations apply to avoid potential errors. Then attach a statement explaining that the amount being claimed is really for Section 863(b). | 2024-01-30 | 2024-01-30 | RESOLVED
2022-12-15 | 2022 | Form 3468 | Dependency | Form 3468 line 12cc did not get changed to remove element "BssWindPropPlacedInSrvcYr4Amt" and to change element "CalcBssWindPropPlcdSrvcYr4Amt" for TY 22 PY 23. | An attachment is required to explain the catch all credits, per the new instructions, and this explanation will be attached at the form level. | 2024-01-30 | 2024-01-30 | RESOLVED
2022-12-15 | 2022 | Form 3468 | Dependency | Form 3468 line 12bb did not get changed to remove element "BssWindPropPlacedInSrvcYr4Amt" and to change element "CalcBssWindPropPlcdSrvcYr4Amt" for TY 22 PY 23. | An attachment is required to explain the catch all credits, per the new instructions, and this explanation will be attached at the form level. | 2024-01-30 | 2024-01-30 | RESOLVED
2022-12-08 | 2022 | Form 1040 (SCH EIC) | Business Rules | Business Rule SEIC-F1040-536-03 has not been updated to change "qualifying widow(er)" language to "surviving spouse" language. | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-08 | 2022 | Form 8908 | Stylesheet | Taxpayers are incorrectly taking this credit for homes they did not own. A note was added to the Form 8908 for this but MeF was not able to update our stylesheet. | Review note section above line 1a on Form 8908 for additional information and see instructions. An update to our stylesheets will be done in processing year 2024. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-12-02 | 2022 | Form 1040 (SCH 1) | Stylesheet | Form 1040, Schedule 1, Line 8b displays as Gambling winnings, instead of Gambling. Line 8u displays as Certain wages from penal institutions, instead of Wages earned while incarcerated. | No impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-12-02 | 2022 | Form 8854 | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No impact at this time. | 2023-04-19 | 2023-03-19 | RESOLVED
2022-12-02 | 2022 | Form 8854 | Schema | Form 8854, Section B, Line 6 group name 'PensionFromSrvcPerfInUSGrp' did not get updated to reflect current line information for Pensions or similar retirement arrangements (both U.S. and foreign). Section B, Line 7 group name 'PensionFromSrvcPerfOutsdUSGrp' did not get updated to reflect current line information for Deferred compensation (including stock options). | Please utilize the existing Schema fields for Form 8854, Part II, Section B, Line 6 and 7. | 2024-01-01 | 2024-01-14 | RESOLVED
2022-12-01 | 2022 | Form 1040-NR | Stylesheet | Form 1040-NR Stylesheet is displaying the filing status Qualifying Widow(er) instead of Qualifying Surviving Spouse. | No Impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-12-01 | 2022 | Form 1040-NR (SCH NEC) | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No Impact at this time. | 2023-03-19 | 2023-03-21 | RESOLVED
2022-12-01 | 2022 | Form 1040-NR (SCH A) | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No Impact at this time. | 2023-03-19 | 2023-03-20 | RESOLVED
2022-12-01 | 2022 | Form 1040-NR (SCH OI) | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No Impact at this time. | 2023-03-19 | 2023-03-22 | RESOLVED
2022-12-01 | 2022 | Form 461 | Business Rules | Business rules F461-002-01 does not show the correct threshold values for TY2022. The current business rule shows the values of 262,000 and 524,000. The correct threshold amounts of 270,000 (single) and 540,000 (married filing jointly) will be updated in March 2023 for 1040 returns. | Business rule was disabled 2/5/2023, and it will be updated in 3/19/2023 in the production environment. In order to bypass the schema, do not input any amount on Form 461 Line 15. On line 16 consider the appropriate amount from line 15 (270,000 or 540,000) and add the amount with line 14 as instructed on line 16. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-12-01 | 2022 | Form 461 | Schema | Form 461 line 15 does not show the correct threshold values for TY2022. The schema currently shows 'FilingStatusThresholdCd' of 262,000 and 524,000 and they should have the value of "270,000" and "540,000". | The schema will show the correct tax year values of 270,000 and 540,000 on 3/19/2023 in the production environment. Please do not input any amounts on line 15 for tax year 2022. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-12-01 | 2022 | Form 461 | Business Rules | Business rule F461-004-01 does not show the correct threshold value for TY2022. The current business rule shows the value of 262,000. The correct threshold amount of 270,000 will be updated 2/19/2023 for 1041 returns. | Business rule will be disabled for Form 1041 returns on 2/19/2023. Form 1040NR returns could be filed and are not being impacted by this business rule. Once the rule is disabled on 2/19/2023 for 1041 returns, you can leave line 15 blank. On line 16, consider the appropriate amount from line 15 (270,000), and add the amount with line 14 as instructed on Line 16. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-12-01 | 2022 | Form 5471 (SCH G-1) | Schema | Revised instructions for Form 5471 Schedule G-1 now include a new attachment requirement for Line 6b, but there is not currently an attachment dependency for the line in the schema. | There is currently a binary attachment at theform level that can be used to substantiate the information needed for line 6b. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-11-30 | 2022 | Form W-2 | Business Rules | Business rule FW2-001-02 will reject for TY 2022 returns when the total of 'WagesAmt' for all Form W-2s is more than ‘WagesSalariesAndTipsAmt' in the return. | Business rule FW2-001-02 will be modified in PY2023. | 2023-04-30 | 2023-02-05 | RESOLVED
2022-11-30 | 2022 | Form 8839 | Stylesheet | Line 29 hasn’t been updated for Tax Year 2022. Line 29 should read: Taxable benefits. Is line 28 more than line 21? if No: Subtract line 28 from line 21. Also, include this amount, if more than zero, on line 1f of Form 1040, 1040-SR, or 1040-NR. if Yes: Subtract line 21 from line 28. Enter the result as a negative number. Also, enter the result on line 1f of Form 1040, 1040-SR, or 1040-NR. | No impact at this time. | 2023-03-19 | 2023-03-20 | RESOLVED
2022-11-30 | 2022 | Form 8919 | Stylesheet | Line 6 hasn’t been updated for Tax Year 2022. Line 6 should read:Total wages. Combine lines 1 through 5 in column (f). Enter here and on Form 1040, 1040-SR, or 1040-NR, line 1g. | No impact at this time. | 2023-03-19 | 2023-03-20 | RESOLVED
2022-11-30 | 2022 | Form 1118 | Schema | The IRS1118/IRS1118ScheduleH/TotDedAllocApprtn245ADivGrp/Section951AIncomeCd field in Schedule H Part III Line 2a column (f) was inadvertently made mandatory in the schema. The field should not be mandatory and will be corrected in a future release. | Until resolved, please input simply "951A" in the field to allow processing. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-30 | 2022 | Form 8854 | Business Rules | Form 8854, Part II, Section C was updated to reflect the current net income tax liability amount for Property Owned on Date of Expatriation from $172,000 to $178,000. | The business rule, F8854-017-05 will be corrected in PY2023 | 2023-04-19 | 2023-03-19 | RESOLVED
2022-11-30 | 2022 | Form 1040 | Stylesheet | Form 1040SS/PR Stylesheet is displaying the filing status Qualifying Widow(er) instead of Qualifying Surviving Spouse. | No impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-30 | 2022 | Form 499 R-2/W-2PR | Stylesheet | Form 499R2/W2PR tax year displays as 2021 instead of 2022. Line 6, Section F displays as others instead of Empleo directo (Ver instrucciones) Direct employment (See instructions) (i) Horas trabajadas Hours worked (ii) EIN. Line 6, Section G isn't displaying. | No impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-30 | 2022 | Form 8859 | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No Impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-30 | 2022 | Form 499 R-2/W-2PR | Schema | Form 499R2/W2PR XML Schema, Line 6, Section A-F will display with the same line description as Tax Year 2021 instead of description for Tax Year 2022. Line 6, Section G will not display. | Please do not complete an entry for Form 499R2/W2PR Line 6, Section G. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-30 | 2022 | Form 1040 | Schema | Form 1040SS/PR Part 1, Line 1, enumeration "5" definition is displaying Qualifying Widow(er) instead of Qualifying Surviving Spouse. | No impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-29 | 2022 | Form 1040 | Business Rules | For BR F1040-016-08 there is a typo in the element name 'HouseholdEmployeeWages'. The element name should be 'HouseholdEmployeeWagesAmt'. | No impact at this time, the coding of the rule is correct. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-28 | 2022 | Form 1065 | Schema and Stylesheet | The Form 1065 will show Schedule B, Line 29 as "Reserved for future use". However, MeF Stylesheets and schema reflect a question and element name for this line. | Disregard the Form 1065, Schedule B, line 29 question Schema and stylesheet in MeF. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-11-21 | 2022 | Form 1120 | SOR | TY2022v5.0 Business Rule package: Form 1120 Amended -The Error Category, Severity and Rule Status columns are out of sync with the addition of new rule FPYMT-119. Form 1120-F and Form 1120-S - The amended rules were not included in the package. | Inserting a row after FPYMT-119 will correct the out of sync issue in the Form 1120 Amended TY2022v5.0 document. If necessary, please contact the External for a corrected TY2022v5.0 package. A new business rule package is tentatively scheduled for the end of November and will reflect all corrected files. | 2022-12-01 | 2022-11-22 | RESOLVED
2022-11-18 | 2022 | Form 1040 | Stylesheet | Digital Assets section added. Question should read: At any time during 2022, did you: (a) receive (as a reward, award, or payment for property or services); or (b) sell, exchange, gift, or otherwise dispose of a digital asset (or a financial interest in a digital asset)? (See instructions.)Hyperlink in Amount You Owe section should read:www.irs.gov/Payments | No impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-18 | 2022 | Form 1040 | Stylesheet | Hyperlink in Amount You Owe section should read:www.irs.gov/Payments | No impact at this time. | 2023-06-18 | 2023-06-18 | RESOLVED
2022-11-18 | 2022 | Form 1040-SR | Stylesheet | Hyperlink in Amount You Owe section is incorrectly displaying as: www.IRS.gov/Payment. Correct hyperlink should be: www.irs.gov/Payments. | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-11-10 | 2022 | Form 1040 | Stylesheet | Form 1040 Stylesheet is displaying the filing status Qualifying Widow(er) instead of Qualifying Surviving Spouse | No impact at this time. | 2023-03-19 | 2023-03-19 | RESOLVED
2022-11-10 | 2022 | Form 1040 | Schema | The ‘wagesNotShownLitOnlyCd’ and the enumeration "FB" that are used to identify an amount attributable to Fringe Benefits is only located on Line 1h of the TY2022 Form 1040 Schema. Fringe Benefits are now also reportable on line 1a. | Use the ‘wagesNotShownLitOnlyCd’ and enumeration "FB" to identify that an amount attributable to a Fringe Benefit is included within an amount reported on Line 1h and/or line 1a. | 2024-01-31 | 2024-01-31 | RESOLVED
2022-11-10 | 2022 | Form 1040-SR | Stylesheet | Form 1040-SR Stylesheet is displaying Sch. B in bubble instead of Schedule B, and Line 16 is displaying Form 4972 instead of Form(s) 4972. Per the early draft, the lines available on page 1 and page 2 have changed; page 1 ends on line 11 instead of line 7, and page 2 begins on line 12 instead of line 8; page 2 ends on line 33. | No impact at this time. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-11-08 | 2022 | Form 8992 (SCH A) | Business Rules | The 2022v3.0 Secure Object Repository distribution did not include the SA-F8992-003 on 1120 PDF documents. The excel document does include the SA-F8992-003. | The 2022v5.0 Secure Object Repository distribution has business rule SA-F8992-003 on 1120 PDF document and excel file. | 2022-11-14 | 2023-02-02 | RESOLVED
2022-11-08 | 2022 | Form 8992 (SCH B) | Business Rules | The 2022v3.0 Secure Object Repository distribution did not include the SB-F8992-005 on 1120 PDF documents. The excel document does include the SB-F8992-005. | The 2022v5.0 Secure Object Repository distribution has business rule SB-F8992-005 on 1120 PDF document and excel file. | 2022-11-14 | 2023-02-02 | RESOLVED
2022-11-08 | 2022 | Form 8992 (SCH B) | Schema | The Instructions for Form 8992 state that Part II of Form 8992 Schedule B is not mandatory. However, the current TY2022 schema in MeF for Form 8992 requires an entry. | If the taxpayer/preparer does not have any information or data to input in Part II and needs to bypass this section, then taxpayers should enter “Information Not required per Instructions” in column (a) and “00-0000000” in column (b) of Part II as a temporary solution for TY2022. | 2024-01-01 | 2023-04-13 | RESOLVED
2022-11-07 | 2022 | Form 6252 | Schema | Form 6252, Line 4 verbiage has been revised to capture if the taxpayer sold the property to an intermediary. Software Developer's and Taxpayers expected PropSoldRltdPartyMrktblSecInd to be deleted and a new element created for the new verbiage on line 4. | We reached out to the Tax Law Specialist (TLS) and confirmed that we were not required to make the update to Form 6252 for Tax Year 2022, We will make a schema change for the new element for Tax Year 2023. Please attach a General Dependency Statement, including the name and address of the intermediary to the parent form (1040, 1040-NR, 1041, 1065, 1120, 1120-F or 1120-S) which you are attaching the Form 6252. | 2023-06-20 | 2023-06-18 | RESOLVED
2022-11-04 | 2022 | Form 3468 | Schema | Form 3468 line 7 elements "BssQlfyInvstAdvncEnergyAmt and CalcBssQlfyInvstAdvncEnergyAmt" for TY 22 PY 23 did not get changed to remove the Advanced Energy Project credit and add the CHIPs (Creating Helpful Incentives to Produce Semiconductors and Science) credit. | No Impact at this time. The work around for TY2022 PY2023 is to put the Advanced Manufacturing Investment credit amount on line 7. The schema will be updated in early PY 2024. | 2024-01-30 | 2024-01-30 | RESOLVED
2022-11-04 | 2022 | Form 8864 | Schema | Form 8864 Lines 8 element 'SustainableAviationFuelCrGrp' and Line 10 element 'BiodieselRenewableFuelsAmt' have not been changed to include "mixture" to the element name. | No Impact at this time. The instructions will give guidelines for the sustainable aviation fuel mixture credit on lines 8 and 10 workaround for TY2022 PY 2023. The schema will be updated in early PY 2024. | 2024-01-30 | 2024-01-30 | RESOLVED
2022-11-04 | 2022 | Form 3468 | Dependency | Form 3468 line 12hh did not get changed to remove element "BssWindPropPlacedInSrvcYr4Amt" and to change element "CalcBssWindPropPlcdSrvcYr4Amt" for TY 22 PY 23. Also, the schema was not updated to include a statement attachment. | An attachment is required to explain the catch all credits, per the new instructions, and this explanation will be attached at the form level. | 2024-01-30 | 2024-01-30 | RESOLVED
2022-10-25 | 2022 | Form 1042 | Schema | The element ‘SpecialConditionDesc’ was erroneously omitted from the Form 1042 schema for Tax Year 2022 | If you have a circumstance meeting the criteria for: "Dividend Equivalent Partnership" OR "3121 Agreement" OR "VCP", include the notation in a General Dependency Small and include it in the submission. The update to include this missing schema element has been placed in a UWR for implementation later in PY2023 | 2023-03-30 | 2023-12-04 | RESOLVED
2022-10-20 | 2022 | Form 5329 | Schema | Tax Year 2022 Form 5329, Additional Taxes on Qualified Plans, Instructions, contains additional enumerations for line 2 of which include Exception Reason Codes 13-21 and 99. Currently, the schema does not include these new codes. | If Exception Reason Codes 13-21 or 99 apply, leave ‘EarlyDistriExceptionReasonCd’ blank. | 2024-01-01 | 2024-01-01 | RESOLVED
2022-10-14 | 2022 | Form 1120 | Business Rules | Business Rule FPYMT-034-01: "Payment Amount" in the "IRS Payment" [IRS Payment] must not be greater than 200% of Form 1120, Line 34, but cannot be greater than 99,999,999. references the wrong line number. It should reference line 35. | Schema will be updated in PY2023. | 2023-02-09 | 2023-02-09 | RESOLVED
2022-10-12 | 2022 | Form 3468 | Schema | Form 3468 Line 6 elements "QlfyGasificationPropBssAmt and CalcQlfyGasificationPropBssAmt" did not get changed to add the Advanced Energy Project credit for TY 22 PY 2023. | No Impact at this time. The workaround for TY 22 PY 23 is to input the Advanced Energy Project credit on line 6. The schema will be updated in early PY 2024. | 2024-01-30 | 2024-01-30 | RESOLVED
2022-10-05 | 2022 | Form 1040 (SCH B) | Stylesheet | Form 1040 Schedule B, Line 7b has the word “list” in the sentence instead of the word “enter”.IS: If you are required to file FinCEN Form 114, list the name(s) of the foreign country(-ies) where the financial account(s) are located.S/B: If you are required to file FinCEN Form 114, enter the name(s) of the foreign country(-ies) where the financial account(s) are located. | No Impact at this time. | 2024-01-01 | 2023-07-18 | RESOLVED
2022-10-04 | 2022 | Form SSA 1042-S | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No Impact at this time. | 2024-01-01 | 2024-01-29 | RESOLVED
2022-10-04 | 2022 | Form RRB 1042-S | Stylesheet | The tax year throughout the form does not reflect the change from 2021 to 2022. | No Impact at this time. | 2024-01-01 | 2024-01-29 | RESOLVED
2022-09-29 | 2022 | Form 5695 | Schema | Form 5695 for Tax Year 2022 was revised to rename the Residential Energy Efficient Property Credit to Residential Clean Energy Credit and the Nonbusiness Energy Property Credit to Energy Efficient Home Improvement Credit. | Schema will be updated in early PY2023. | 2023-04-30 | 2023-04-20 | RESOLVED
2022-09-29 | 2022 | Form 5695 | Business Rules | Form 5695 for Tax Year 2022 was revised to rename the Residential Energy Efficient Property Credit to Residential Clean Energy Credit and the Nonbusiness Energy Property Credit to Energy Efficient Home Improvement Credit. | Business Rules will be updated in early PY2023. | 2023-04-30 | 2023-04-20 | RESOLVED
2022-09-29 | 2022 | Form 8915-F | Schema | There are several disasters listed on Form 8915-F Appendix B Instructions that do not follow the format of element 'FEMADisasterDeclarationNum'. For example: Severe Storms, Flooding, Landslides and Mudslides in Alaska is shown on Appendix B as (4585-DR-AK) | The format of schema element 'FEMADisasterDeclarationNum' needs to be written (([D][R])¦([E][M]))-[0-9]{4})--[2 letter state abbreviation]. The example needs to be written out on schema as DR-4585-AK. Schema will be updated in Processing Year 2024/Tax year 2023. | 2024-01-08 | 2024-01-16 | RESOLVED
2022-09-27 | 2022 | Form 8886 | Schema | The e-file type for Line 1c, TaxShelterRegistrationType, only allows for 7 or 11 character combinations. A TP with 8 characters is being rejected. | A correction will be made in PY2023 to allow for an 8 character combination, BUT it will not be available in production until Tax Year 2023 / Processing Year 2024. The temporary solution will be to utilize GeneralDependencySmall to report. | 2024-01-01 | 2023-07-19 | RESOLVED
2022-09-22 | 2022 | Form 6627 | Schema | The current `RatioType' e-file type for Part III IRS No. 17 will not allow a value greater than 1.0 which is causing Business Rule X0000-005 to trigger. | We do not have a workaround at this time and we are unable to make updates to the schema. Please file a paper return for the 3rd & 4th quarters if you are reporting items under IRS No. 17. We will list this as a Known Issue and keep Software Developers posted on when the schemas have been updated. TY2022 will not be updated. The schema was updated for TY2023v1.0. | 2022-10-01 | 2022-10-24 | RESOLVED
2022-09-09 | 2022 | Form 5471 (SCH P) | Schema | The element ‘ForeignCorpMissingEINReasonCd’ was erroneously left in the Form 5471 Schedule P schema for Tax Year 2022. | The schema for Form 5471 Schedule P should be corrected to remove the element ForeignCorpMissingEINReasonCd before production begins for TY2022. If not, Software developers can input the enumeration "APPLD FOR" for the element "ForeignCorpMissingEINReasonCd" for Form 5471 Schedule P submissions with a ForeignCorporationEIN. | 2022-10-15 | 2022-12-08 | RESOLVED